## Executive Summary
DORA Compliance Framework - Executive Summary
Report Date: | August 05, 2025
Overall Compliance Status
Total Requirements: | 75
Not Started: | 65 (87%)
In Progress: | 8 (11%)
Completed: | 2 (3%)
Risk Assessment
Critical Priority Items: | 15
High Priority Items: | 35
Medium Priority Items: | 20
Low Priority Items: | 5
Key Implementation Dates
DORA Effective Date: | January 17, 2025
Days Remaining: | 165
Next Major Milestone: | Board Approval - October 15, 2024
Critical Actions Required
1. Immediate board engagement and approval
2. Establish DORA program management office
3. Complete ICT asset inventory
4. Implement incident response procedures
5. Enhance third-party risk management
Budget Requirements (Estimated)
Technology Infrastructure: | €2,500,000
External Consulting: | €1,200,000
Staff Training: | €300,000
Regulatory Compliance: | €500,000
Total Estimated Cost: | €4,500,000
Resource Requirements
Full-time Program Manager: | 1
IT Risk Specialists: | 3
Security Analysts: | 2
Compliance Officers: | 2
Business Analysts: | 2
Key Risks
- Insufficient time for full implementation
- Resource constraints and competing priorities
- Third-party vendor readiness
- Regulatory interpretation uncertainty
- Integration with existing systems

## DORA Compliance
Sheet | Section | Category | Requirement | Article Reference | Description | Implementation Status | Priority | Responsible Party | Target Date | Current Status | Gap Analysis | Action Required | Evidence/Documentation | Notes
Executive Summary | Overview | Regulatory Overview | DORA Introduction | Art. 1 | Digital Operational Resilience Act implementation for financial entities | Not Started | High | Chief Risk Officer | 2024-12-31 | Planning | Full framework needed | Develop comprehensive DORA strategy | Regulatory text review | EU regulation effective January 2025
Executive Summary | Overview | Scope | Applicable Entities | Art. 2 | Credit institutions investment firms insurance companies | Not Started | High | Legal Department | 2024-10-31 | Assessment | Entity classification needed | Confirm DORA applicability | Legal opinion | Include all subsidiaries
Executive Summary | Overview | Timeline | Implementation Deadline | Art. 64 | Compliance required by January 17 2025 | Not Started | Critical | Program Management Office | 2024-12-31 | Planning | 6 months remaining | Accelerate implementation | Project timeline | Consider phased approach
ICT Risk Management | Framework | Governance | ICT Risk Management Framework | Art. 6 | Establish comprehensive ICT risk management framework | Not Started | High | IT Risk Manager | 2024-11-30 | Planning | Framework development needed | Create ICT risk framework | Framework document | Align with existing risk frameworks
ICT Risk Management | Framework | Governance | Board Oversight | Art. 6 | Board and senior management oversight of ICT risks | Not Started | High | Board of Directors | 2024-10-15 | Planning | Board education needed | Conduct board training | Board minutes | Include ICT risk in board agenda
ICT Risk Management | Framework | Strategy | ICT Strategy | Art. 6 | Define ICT strategy aligned with business strategy | Not Started | High | CTO | 2024-11-15 | Planning | Strategy development needed | Develop ICT strategy | Strategy document | Link to business objectives
ICT Risk Management | Framework | Risk Appetite | ICT Risk Appetite | Art. 6 | Define ICT risk appetite and tolerance levels | Not Started | High | Chief Risk Officer | 2024-11-30 | Planning | Risk appetite definition needed | Define risk thresholds | Risk appetite statement | Quantify risk limits
ICT Risk Management | Framework | Policies | ICT Risk Policies | Art. 6 | Establish ICT risk management policies | Not Started | Medium | IT Risk Manager | 2024-12-15 | Planning | Policy development needed | Create risk policies | Policy documents | Regular policy reviews
ICT Risk Management | Controls | Asset Management | ICT Asset Inventory | Art. 8 | Maintain comprehensive ICT asset inventory | Not Started | High | IT Asset Manager | 2024-10-31 | Planning | Asset discovery needed | Implement asset management | Asset register | Include all ICT assets
ICT Risk Management | Controls | Asset Management | Asset Classification | Art. 8 | Classify ICT assets based on criticality and sensitivity | Not Started | High | IT Security Manager | 2024-11-15 | Planning | Classification scheme needed | Develop classification framework | Classification matrix | Risk-based approach
ICT Risk Management | Controls | Change Management | ICT Change Management | Art. 8 | Implement robust ICT change management processes | Not Started | Medium | IT Operations Manager | 2024-11-30 | Planning | Process enhancement needed | Strengthen change controls | Change management procedures | Include risk assessment
ICT Risk Management | Controls | Configuration Management | Configuration Management | Art. 8 | Maintain secure configuration of ICT systems | Not Started | Medium | IT Security Manager | 2024-12-15 | Planning | Configuration standards needed | Develop security baselines | Configuration standards | Automated compliance checking
ICT Risk Management | Controls | Patch Management | Security Patch Management | Art. 8 | Implement timely security patch management | Not Started | High | IT Security Manager | 2024-10-31 | Planning | Patch process improvement | Enhance patch management | Patch management policy | Critical patch SLAs
ICT Risk Management | Monitoring | Risk Monitoring | Continuous Risk Monitoring | Art. 8 | Continuously monitor ICT risks and controls | Not Started | High | IT Risk Manager | 2024-11-30 | Planning | Monitoring tools needed | Deploy risk monitoring | Monitoring dashboard | Real-time risk visibility
ICT Risk Management | Monitoring | Performance Monitoring | ICT Performance Monitoring | Art. 8 | Monitor ICT system performance and availability | In Progress | Medium | IT Operations Manager | 2024-10-15 | Implementation | Enhancement needed | Improve monitoring tools | Performance reports | 24/7 monitoring capability
ICT Risk Management | Monitoring | Security Monitoring | Security Event Monitoring | Art. 8 | Monitor security events and incidents | In Progress | High | IT Security Manager | 2024-10-31 | Implementation | SIEM enhancement needed | Upgrade security monitoring | SIEM logs | SOC capability
ICT Incident Management | Framework | Incident Response | Incident Response Framework | Art. 17 | Establish comprehensive incident response framework | Not Started | High | CISO | 2024-10-31 | Planning | Framework development needed | Create incident response plan | Incident response plan | Include business continuity
ICT Incident Management | Framework | Classification | Incident Classification | Art. 17 | Define incident classification and severity levels | Not Started | High | IT Security Manager | 2024-10-15 | Planning | Classification scheme needed | Develop severity matrix | Classification criteria | Business impact focus
ICT Incident Management | Framework | Escalation | Escalation Procedures | Art. 17 | Define incident escalation procedures and timelines | Not Started | Medium | IT Operations Manager | 2024-10-31 | Planning | Procedures development needed | Create escalation matrix | Escalation procedures | Clear communication paths
ICT Incident Management | Response | Detection | Incident Detection | Art. 17 | Implement automated incident detection capabilities | Not Started | High | IT Security Manager | 2024-11-15 | Planning | Detection tools needed | Deploy detection systems | Detection capabilities | AI/ML enhancement
ICT Incident Management | Response | Response Team | Incident Response Team | Art. 17 | Establish dedicated incident response team | Not Started | High | CISO | 2024-10-15 | Planning | Team formation needed | Form response team | Team structure | 24/7 availability
ICT Incident Management | Response | Communication | Incident Communication | Art. 17 | Define incident communication procedures | Not Started | Medium | Communications Manager | 2024-10-31 | Planning | Communication plan needed | Develop communication plan | Communication templates | Stakeholder mapping
ICT Incident Management | Reporting | Internal Reporting | Internal Incident Reporting | Art. 18 | Report incidents to internal stakeholders | Not Started | High | IT Risk Manager | 2024-10-31 | Planning | Reporting process needed | Create reporting procedures | Reporting templates | Timely escalation
ICT Incident Management | Reporting | Regulatory Reporting | Regulatory Incident Reporting | Art. 19 | Report major incidents to supervisory authorities | Not Started | Critical | Compliance Officer | 2024-10-15 | Planning | Regulatory process needed | Establish regulatory reporting | Reporting procedures | 72-hour timeline
ICT Incident Management | Reporting | Documentation | Incident Documentation | Art. 17 | Maintain comprehensive incident documentation | Not Started | Medium | IT Operations Manager | 2024-11-30 | Planning | Documentation system needed | Implement incident tracking | Documentation system | Lessons learned capture
Digital Operational Resilience Testing | Framework | Testing Strategy | DORT Strategy | Art. 24 | Develop digital operational resilience testing strategy | Not Started | High | IT Risk Manager | 2024-11-30 | Planning | Strategy development needed | Create DORT strategy | Testing strategy | Risk-based approach
Digital Operational Resilience Testing | Framework | Testing Program | Testing Program | Art. 24 | Establish comprehensive testing program | Not Started | High | IT Security Manager | 2024-12-15 | Planning | Program development needed | Design testing program | Testing program | Annual testing cycle
Digital Operational Resilience Testing | Framework | Testing Types | Testing Types | Art. 25 | Define various types of resilience testing | Not Started | Medium | IT Operations Manager | 2024-11-15 | Planning | Testing taxonomy needed | Define testing types | Testing framework | Include all scenarios
Digital Operational Resilience Testing | General Testing | Vulnerability Testing | Vulnerability Assessments | Art. 25 | Conduct regular vulnerability assessments | In Progress | High | IT Security Manager | 2024-10-31 | Implementation | Enhanced testing needed | Expand vulnerability testing | Vulnerability reports | Quarterly assessments
Digital Operational Resilience Testing | General Testing | Penetration Testing | Penetration Testing | Art. 25 | Perform regular penetration testing | In Progress | High | External Security Firm | 2024-12-31 | Implementation | Annual testing planned | Conduct annual pen testing | Penetration test reports | Independent testing
Digital Operational Resilience Testing | General Testing | Scenario Testing | Scenario-based Testing | Art. 25 | Conduct scenario-based resilience testing | Not Started | Medium | IT Risk Manager | 2024-12-15 | Planning | Scenario development needed | Develop test scenarios | Test scenarios | Business impact scenarios
Digital Operational Resilience Testing | Advanced Testing | TLPT Preparation | TLPT Readiness | Art. 26 | Prepare for threat-led penetration testing | Not Started | High | CISO | 2025-06-30 | Planning | TLPT preparation needed | Prepare for TLPT | TLPT framework | Regulatory requirement
Digital Operational Resilience Testing | Advanced Testing | Red Team Testing | Red Team Exercises | Art. 26 | Conduct red team exercises | Not Started | Medium | External Security Firm | 2025-03-31 | Planning | External provider needed | Engage red team services | Red team reports | Simulate real attacks
Digital Operational Resilience Testing | Advanced Testing | Testing Frequency | Testing Schedule | Art. 25 | Define testing frequency and scheduling | Not Started | Medium | IT Risk Manager | 2024-11-30 | Planning | Schedule development needed | Create testing calendar | Testing schedule | Risk-based frequency
ICT Third-party Risk | Framework | Risk Management | Third-party Risk Framework | Art. 28 | Establish ICT third-party risk management framework | Not Started | High | Vendor Risk Manager | 2024-11-15 | Planning | Framework development needed | Create vendor risk framework | Vendor risk framework | Due diligence processes
ICT Third-party Risk | Framework | Due Diligence | Due Diligence Process | Art. 30 | Implement comprehensive due diligence processes | Not Started | High | Procurement Manager | 2024-10-31 | Planning | Process enhancement needed | Enhance due diligence | Due diligence procedures | Risk assessment integration
ICT Third-party Risk | Framework | Contracting | Contract Management | Art. 30 | Enhance ICT service provider contract management | Not Started | High | Legal Department | 2024-11-30 | Planning | Contract template needed | Develop DORA contracts | Contract templates | Include exit clauses
ICT Third-party Risk | Critical Providers | Identification | Critical Provider Identification | Art. 28 | Identify and classify critical ICT third-party providers | Not Started | Critical | Vendor Risk Manager | 2024-10-15 | Planning | Provider assessment needed | Assess provider criticality | Provider inventory | Risk-based classification
ICT Third-party Risk | Critical Providers | Oversight | Enhanced Oversight | Art. 30 | Implement enhanced oversight of critical providers | Not Started | High | Vendor Risk Manager | 2024-11-30 | Planning | Oversight program needed | Design oversight program | Oversight procedures | Continuous monitoring
ICT Third-party Risk | Critical Providers | Exit Strategies | Exit Planning | Art. 28 | Develop exit strategies for critical providers | Not Started | High | Business Continuity Manager | 2024-12-15 | Planning | Exit plans needed | Create exit strategies | Exit plans | Alternative providers
ICT Third-party Risk | Monitoring | Performance Monitoring | Provider Performance Monitoring | Art. 30 | Monitor ICT third-party provider performance | Not Started | Medium | Vendor Risk Manager | 2024-11-30 | Planning | Monitoring system needed | Implement provider monitoring | Monitoring dashboard | SLA tracking
ICT Third-party Risk | Monitoring | Risk Monitoring | Provider Risk Monitoring | Art. 30 | Continuously monitor third-party risks | Not Started | High | IT Risk Manager | 2024-11-15 | Planning | Risk monitoring needed | Deploy risk monitoring | Risk assessments | Regular risk reviews
ICT Third-party Risk | Monitoring | Compliance Monitoring | Provider Compliance Monitoring | Art. 30 | Monitor third-party compliance with requirements | Not Started | Medium | Compliance Officer | 2024-12-31 | Planning | Compliance tracking needed | Track provider compliance | Compliance reports | Regular audits
Information Sharing | Framework | Information Sharing | Cyber Threat Information Sharing | Art. 20 | Participate in cyber threat information sharing | Not Started | Medium | IT Security Manager | 2024-12-31 | Planning | Sharing mechanisms needed | Join threat sharing groups | Sharing agreements | Industry collaboration
Information Sharing | Framework | Threat Intelligence | Threat Intelligence Program | Art. 20 | Establish threat intelligence capabilities | Not Started | High | Threat Intelligence Analyst | 2024-11-30 | Planning | Intelligence program needed | Develop threat intelligence | Intelligence feeds | Actionable intelligence
Information Sharing | Framework | Industry Collaboration | Industry Collaboration | Art. 20 | Collaborate with industry peers on cyber threats | Not Started | Medium | CISO | 2024-12-15 | Planning | Collaboration framework needed | Establish industry partnerships | Partnership agreements | Knowledge sharing
Governance | Oversight | Management Body | Management Body Oversight | Art. 6 | Ensure management body oversight of ICT risks | Not Started | Critical | Board of Directors | 2024-09-30 | Planning | Board engagement needed | Enhance board oversight | Board charter updates | Regular risk reporting
Governance | Oversight | Senior Management | Senior Management Responsibilities | Art. 6 | Define senior management ICT risk responsibilities | Not Started | High | CEO | 2024-10-15 | Planning | Role clarification needed | Define management roles | Role descriptions | Clear accountability
Governance | Oversight | Risk Committee | ICT Risk Committee | Art. 6 | Establish ICT risk committee or enhance existing | Not Started | Medium | Chief Risk Officer | 2024-11-30 | Planning | Committee establishment needed | Form ICT risk committee | Committee charter | Regular meetings
Governance | Policies | ICT Policy Framework | ICT Policy Framework | Art. 6 | Establish comprehensive ICT policy framework | Not Started | High | Chief Risk Officer | 2024-11-30 | Planning | Policy framework needed | Develop policy framework | Policy inventory | Regular reviews
Governance | Policies | Risk Policies | ICT Risk Policies | Art. 6 | Develop specific ICT risk management policies | Not Started | High | IT Risk Manager | 2024-11-15 | Planning | Policy development needed | Create ICT risk policies | Policy documents | Board approval
Governance | Policies | Security Policies | ICT Security Policies | Art. 8 | Enhance ICT security policies and procedures | Not Started | Medium | CISO | 2024-12-15 | Planning | Policy updates needed | Update security policies | Security policies | Regular updates
Governance | Documentation | Framework Documentation | Framework Documentation | Art. 6 | Document ICT risk management framework | Not Started | Medium | IT Risk Manager | 2024-12-31 | Planning | Documentation needed | Create framework documentation | Framework documents | Version control
Governance | Documentation | Procedure Documentation | Procedure Documentation | Art. 8 | Document ICT risk management procedures | Not Started | Medium | IT Operations Manager | 2024-12-15 | Planning | Procedure documentation needed | Document procedures | Procedure manuals | Regular updates
Governance | Documentation | Training Documentation | Training Materials | Art. 6 | Develop ICT risk management training materials | Not Started | Medium | HR Training Manager | 2024-11-30 | Planning | Training materials needed | Create training content | Training materials | Regular delivery
Training and Awareness | Training Program | Staff Training | ICT Risk Training | Art. 6 | Provide ICT risk management training to staff | Not Started | Medium | HR Training Manager | 2024-12-31 | Planning | Training program needed | Develop training program | Training curriculum | Regular sessions
Training and Awareness | Training Program | Management Training | Management Training | Art. 6 | Provide specialized training to management | Not Started | High | External Training Provider | 2024-11-15 | Planning | Management training needed | Design management training | Training materials | Executive briefings
Training and Awareness | Training Program | Technical Training | Technical Training | Art. 8 | Provide technical ICT risk training | Not Started | Medium | IT Training Manager | 2024-12-15 | Planning | Technical training needed | Develop technical training | Training modules | Hands-on training
Training and Awareness | Awareness Program | Awareness Campaign | ICT Risk Awareness | Art. 6 | Conduct ICT risk awareness campaigns | Not Started | Low | Communications Manager | 2024-12-31 | Planning | Awareness campaign needed | Launch awareness campaign | Campaign materials | Regular communications
Training and Awareness | Awareness Program | Communication | Risk Communication | Art. 6 | Communicate ICT risks throughout organization | Not Started | Medium | Chief Risk Officer | 2024-11-30 | Planning | Communication strategy needed | Develop communication plan | Communication plan | Regular updates
Training and Awareness | Awareness Program | Culture | Risk Culture | Art. 6 | Foster strong ICT risk culture | Not Started | Medium | Chief Risk Officer | 2025-03-31 | Planning | Culture program needed | Build risk culture | Culture initiatives | Long-term commitment
Compliance and Reporting | Regulatory Compliance | Supervisory Reporting | Supervisory Reporting | Art. 54 | Establish supervisory reporting capabilities | Not Started | Critical | Compliance Officer | 2024-10-31 | Planning | Reporting system needed | Build reporting capabilities | Reporting system | Automated reporting
Compliance and Reporting | Regulatory Compliance | Audit Preparation | Audit Readiness | Art. 6 | Prepare for supervisory audits and inspections | Not Started | High | Internal Audit Manager | 2024-11-30 | Planning | Audit preparation needed | Prepare for audits | Audit documentation | Evidence collection
Compliance and Reporting | Regulatory Compliance | Compliance Monitoring | Compliance Monitoring | Art. 6 | Monitor compliance with DORA requirements | Not Started | High | Compliance Officer | 2024-10-15 | Planning | Monitoring system needed | Implement compliance monitoring | Compliance dashboard | Regular assessments
Compliance and Reporting | Internal Reporting | Management Reporting | Management Reporting | Art. 6 | Report ICT risks to management and board | Not Started | High | IT Risk Manager | 2024-10-31 | Planning | Reporting framework needed | Create management reporting | Reporting templates | Regular reporting
Compliance and Reporting | Internal Reporting | Risk Reporting | Risk Reporting | Art. 6 | Establish comprehensive ICT risk reporting | Not Started | Medium | IT Risk Manager | 2024-11-15 | Planning | Risk reporting needed | Develop risk reporting | Risk reports | KRI reporting
Compliance and Reporting | Internal Reporting | Incident Reporting | Incident Reporting | Art. 18 | Report ICT incidents internally | Not Started | High | IT Operations Manager | 2024-10-31 | Planning | Incident reporting needed | Create incident reporting | Incident reports | Timely reporting
Business Continuity | BCP Framework | Business Continuity | ICT Business Continuity | Art. 11 | Integrate ICT considerations into BCP | Not Started | High | Business Continuity Manager | 2024-11-30 | Planning | BCP integration needed | Enhance BCP for ICT | BCP documentation | ICT dependencies
Business Continuity | BCP Framework | Recovery Planning | ICT Recovery Planning | Art. 11 | Develop ICT-specific recovery procedures | Not Started | High | IT Operations Manager | 2024-12-15 | Planning | Recovery plans needed | Create ICT recovery plans | Recovery procedures | RTO/RPO definitions
Business Continuity | BCP Framework | Testing | BCP Testing | Art. 11 | Test business continuity plans including ICT | Not Started | Medium | Business Continuity Manager | 2024-12-31 | Planning | BCP testing needed | Conduct BCP testing | Test results | Regular testing
Business Continuity | Backup and Recovery | Data Backup | Data Backup Strategy | Art. 11 | Implement comprehensive data backup strategy | In Progress | High | IT Operations Manager | 2024-10-31 | Implementation | Backup enhancement needed | Enhance backup systems | Backup procedures | Regular testing
Business Continuity | Backup and Recovery | System Recovery | System Recovery Procedures | Art. 11 | Develop system recovery procedures | Not Started | High | IT Operations Manager | 2024-11-30 | Planning | Recovery procedures needed | Create recovery procedures | Recovery documentation | Automated recovery
Business Continuity | Backup and Recovery | Alternative Sites | Alternative Processing Sites | Art. 11 | Establish alternative processing capabilities | Not Started | Medium | IT Infrastructure Manager | 2025-01-31 | Planning | Site planning needed | Plan alternative sites | Site documentation | Hot/warm/cold sites

## Risk Scoring
Risk Level | Risk Score | Description | Response Required | Escalation Level | Management Attention
Critical | 4 | Immediate threat to business operations, regulatory breach imminent | Immediate action required within 24 hours | Board/CEO | Executive Management
High | 3 | Significant risk to operations or compliance, potential regulatory impact | Action required within 1 week | Senior Management | Division Head
Medium | 2 | Moderate risk with manageable impact on operations | Action required within 1 month | Department Manager | Department Level
Low | 1 | Minor risk with limited operational impact | Action required within 3 months | Team Lead | Team Level
Risk Category | Risk Factor | Weight | Scoring Criteria
Financial Impact | Revenue Impact | 25% | Critical: >€10M, High: €1-10M, Medium: €100K-1M, Low: <€100K
Operational Impact | Service Disruption | 20% | Critical: >24hrs, High: 4-24hrs, Medium: 1-4hrs, Low: <1hr
Regulatory Impact | Compliance Breach | 20% | Critical: Major breach, High: Minor breach, Medium: Warning, Low: No impact
Reputational Impact | Brand Damage | 15% | Critical: National media, High: Industry press, Medium: Local impact, Low: No impact
Customer Impact | Customer Affected | 10% | Critical: >100K customers, High: 10K-100K, Medium: 1K-10K, Low: <1K
Data Impact | Data Breach | 10% | Critical: Personal/Financial, High: Business Critical, Medium: Internal, Low: Public
Status | Definition | Color Code | Action Required
Not Started | No work has begun on this requirement | Red | Immediate planning required
Planning | Requirements analysis and planning in progress | Orange | Continue planning activities
In Progress | Implementation activities underway | Yellow | Monitor progress closely
Completed | Requirement fully implemented and tested | Green | Maintain and monitor
Deferred | Implementation postponed to later phase | Purple | Review deferral reasoning
Priority | Definition | Target Timeframe | Resource Allocation
Critical | Must be completed to avoid regulatory breach | Within 1 month | Highest priority resources
High | Important for compliance and risk reduction | Within 3 months | Dedicated resources
Medium | Needed for complete compliance framework | Within 6 months | Shared resources
Low | Nice to have improvements | Within 12 months | Available resources

## Implementation
Article | Title | Key Requirements | Implementation Timeline | Critical Success Factors
Article 1 | Subject matter and scope | Applies to financial entities, defines scope of regulation | Immediate | Understanding scope and applicability
Article 2 | Definitions | Defines key terms: ICT risk, digital operational resilience, etc. | Immediate | Common understanding of terminology
Article 6 | ICT risk management framework | Establish comprehensive framework, board oversight, policies | By Jan 2025 | Strong governance and leadership commitment
Article 8 | ICT risk management measures | Asset management, change management, configuration | By Jan 2025 | Robust operational processes
Article 11 | Business continuity | BCP integration, backup strategies, recovery procedures | By Jan 2025 | Tested recovery capabilities
Article 17 | ICT-related incident management | Incident response framework, classification, procedures | By Jan 2025 | 24/7 response capability
Article 18 | Classification of ICT-related incidents | Major incident classification criteria and reporting | By Jan 2025 | Clear escalation procedures
Article 19 | Reporting of major ICT-related incidents | Report to supervisory authorities within specific timeframes | By Jan 2025 | Automated reporting capability
Article 20 | Harmonisation of reporting content | Standardized incident reporting format and content | By Jan 2025 | Consistent reporting across entities
Article 24 | General requirements for digital operational resilience testing | DORT strategy, testing program, various testing types | By Jan 2025 | Comprehensive testing framework
Article 25 | Testing of ICT systems | Vulnerability testing, penetration testing, scenario testing | By Jan 2025 | Regular testing schedule
Article 26 | Advanced testing | TLPT requirements for larger entities | By 2026 | Advanced testing capabilities
Article 28 | General principles for ICT third-party risk | Framework for managing third-party ICT risks | By Jan 2025 | Vendor risk management program
Article 30 | Key principles for a sound management of ICT third-party risk | Due diligence, contract management, exit strategies | By Jan 2025 | Enhanced vendor oversight
Article 54 | Supervisory powers and tools | Supervisory reporting and audit capabilities | By Jan 2025 | Regulatory relationship management
Article 64 | Entry into force and application | Regulation applies from January 17, 2025 | Jan 17 2025 | Full compliance readiness
Risk Domain | Key Controls | Implementation Priority | Dependencies
ICT Risk Management | Risk framework and governance | Critical | Board engagement and resources
ICT Risk Management | Asset and change management | High | Asset discovery tools
ICT Risk Management | Configuration and patch management | High | Security tools and processes
Incident Management | Incident response procedures | Critical | 24/7 operational capability
Incident Management | Incident classification system | Critical | Clear escalation matrix
Incident Management | Regulatory reporting capability | Critical | Automated reporting systems
Resilience Testing | Testing strategy and program | High | Testing tools and expertise
Resilience Testing | Regular vulnerability testing | High | Security testing tools
Resilience Testing | Advanced testing capabilities | Medium | External testing providers
Third-party Risk | Vendor risk framework | High | Vendor management system
Third-party Risk | Critical provider oversight | Critical | Enhanced due diligence
Third-party Risk | Contract management | High | Legal and procurement support
Phase | Timeline | Key Deliverables | Success Criteria
Phase 1: Foundation | Sept-Oct 2024 | Framework development, governance setup, critical gaps identified | Board approval and resource allocation
Phase 2: Core Implementation | Nov-Dec 2024 | Risk management processes, incident response, basic testing | Operational capabilities established
Phase 3: Advanced Capabilities | Jan-Mar 2025 | Advanced testing, enhanced monitoring, full compliance | Regulatory audit readiness
Phase 4: Optimization | Apr-Jun 2025 | Process refinement, automation, continuous improvement | Mature operational resilience
Milestone | Target Date | Owner | Dependencies | Status
Board Approval of Framework | 2024-10-15 | Chief Risk Officer | Framework development complete | Not Started
Asset Inventory Complete | 2024-10-31 | IT Asset Manager | Asset discovery tools deployed | Not Started
Incident Response Procedures | 2024-11-15 | CISO | Response team established | Not Started
Regulatory Reporting Capability | 2024-11-30 | Compliance Officer | Reporting system implemented | Not Started
Testing Program Operational | 2024-12-15 | IT Security Manager | Testing tools and procedures ready | Not Started
Third-party Risk Assessment | 2024-12-31 | Vendor Risk Manager | Vendor inventory and classification complete | Not Started
Full DORA Compliance | 2025-01-17 | Program Management Office | All components implemented and tested | Not Started

## KRI & KPI
KRI Name | Category | Metric | Threshold - Green | Threshold - Yellow | Threshold - Red | Frequency | Owner | Data Source
System Availability | Operational | Percentage uptime | >99.9% | 99.5%-99.9% | <99.5% | Daily | IT Operations | Monitoring tools
Mean Time to Recovery | Operational | Hours | <2 hours | 2-8 hours | >8 hours | Per incident | IT Operations | Incident management system
Security Incidents | Security | Number per month | <5 | 5-15 | >15 | Monthly | CISO | SIEM system
Patch Compliance | Security | Percentage of systems | >95% | 90%-95% | <90% | Weekly | IT Security | Patch management system
Vendor Risk Score | Third-party | Weighted average | <2.0 | 2.0-3.0 | >3.0 | Monthly | Vendor Risk Manager | Vendor risk system
Critical Vendor SLA Breaches | Third-party | Number per quarter | 0 | 1-2 | >2 | Quarterly | Vendor Risk Manager | Contract management system
Backup Success Rate | Continuity | Percentage successful | >99% | 95%-99% | <95% | Daily | IT Operations | Backup system
Recovery Test Success | Continuity | Percentage successful | >95% | 90%-95% | <90% | Quarterly | Business Continuity Manager | BCP testing results
Regulatory Findings | Compliance | Number of findings | 0 | 1-2 | >2 | Per audit | Compliance Officer | Audit reports
Training Completion | Training | Percentage of staff | >95% | 90%-95% | <90% | Quarterly | HR Manager | Training system
KPI Name | Category | Metric | Target | Current | Trend | Frequency | Owner
DORA Compliance Score | Overall | Percentage complete | 100% | 25% | Increasing | Monthly | Program Management Office
ICT Risk Assessment Coverage | Risk Management | Percentage of systems assessed | 100% | 40% | Increasing | Quarterly | IT Risk Manager
Incident Response Time | Incident Management | Average minutes to initial response | <30 min | 45 min | Improving | Monthly | CISO
Vulnerability Remediation Time | Security | Average days to remediate critical vulnerabilities | <7 days | 14 days | Stable | Monthly | IT Security Manager
Third-party Risk Assessments | Third-party Risk | Percentage of critical vendors assessed | 100% | 60% | Increasing | Quarterly | Vendor Risk Manager
Business Continuity Test Coverage | Continuity | Percentage of critical processes tested | 100% | 30% | Increasing | Semi-annually | Business Continuity Manager
Staff Training Completion | Training | Percentage of required training completed | 100% | 20% | Increasing | Quarterly | HR Manager
Regulatory Reporting Timeliness | Compliance | Percentage of reports submitted on time | 100% | 85% | Improving | Monthly | Compliance Officer
Stakeholder | Role | RACI - ICT Risk Management | RACI - Incident Management | RACI - Testing | RACI - Third-party Risk | Communication Frequency
Board of Directors | Governance | A | I | I | I | Quarterly
CEO | Executive Leadership | A | A | I | A | Monthly
Chief Risk Officer | Risk Oversight | R | C | C | R | Weekly
CISO | Security Leadership | C | R | R | C | Daily
CTO | Technology Leadership | C | C | R | C | Weekly
IT Risk Manager | Risk Management | R | C | C | C | Daily
IT Operations Manager | Operations | C | R | C | I | Daily
Vendor Risk Manager | Vendor Management | I | I | I | R | Weekly
Compliance Officer | Compliance | C | C | I | C | Weekly
Business Continuity Manager | Continuity | C | C | R | I | Weekly
Report Name | Frequency | Audience | Content | Owner | Distribution Method
DORA Compliance Dashboard | Weekly | Senior Management | Overall compliance status, key metrics, risks | Program Management Office | Executive portal
ICT Risk Report | Monthly | Board and Executive Team | Risk landscape, key risks, mitigation status | Chief Risk Officer | Board pack
Incident Management Report | Monthly | Senior Management | Incident trends, response metrics, lessons learned | CISO | Management meeting
Testing Results Report | Quarterly | IT Leadership | Testing outcomes, vulnerabilities, remediation | IT Security Manager | IT governance meeting
Third-party Risk Report | Quarterly | Risk Committee | Vendor risk landscape, critical vendors, issues | Vendor Risk Manager | Risk committee meeting
Regulatory Reporting | As required | Supervisory Authorities | Major incidents, compliance status, material changes | Compliance Officer | Regulatory portal
R = Responsible (does the work) | A = Accountable (signs off) | C = Consulted (provides input) | I = Informed (kept updated)

## Third Party Risk
Vendor Name | Service Category | Criticality Level | Risk Score | Contract Expiry | SLA Compliance % | Last Assessment Date | Next Review Date | Key Risks | Mitigation Actions
Microsoft | Cloud Infrastructure | Critical | 2.5 | 2025-12-31 | 99.2% | 2024-07-15 | 2024-10-15 | Data sovereignty, service availability | Enhanced monitoring and backup providers
AWS | Cloud Services | Critical | 2.8 | 2024-11-30 | 98.8% | 2024-06-01 | 2024-09-01 | Vendor concentration, data security | Multi-cloud strategy and security controls
Oracle | Database Services | Critical | 3.2 | 2025-03-31 | 97.5% | 2024-05-20 | 2024-08-20 | Legacy system dependency, support | Modernization project and alternative solutions
IBM | Mainframe Services | High | 2.9 | 2024-10-15 | 98.1% | 2024-04-10 | 2024-07-10 | Technology obsolescence, skills | Migration planning and knowledge transfer
Cisco | Network Infrastructure | High | 2.3 | 2025-06-30 | 99.5% | 2024-08-01 | 2024-11-01 | Single point of failure, updates | Redundancy implementation and update procedures
ServiceNow | IT Service Management | Medium | 2.1 | 2025-01-31 | 99.8% | 2024-07-01 | 2024-10-01 | Process dependency, customization | Process documentation and standardization
Assessment Category | Criteria | Weight | Score (1-5) | Weighted Score | Comments
Financial Stability | Credit rating and financial health | 20% | 4 | 0.8 | Strong financial position
Operational Capability | Service delivery and performance | 25% | 3 | 0.75 | Some performance issues noted
Security Posture | Cybersecurity controls and compliance | 20% | 4 | 0.8 | Strong security framework
Business Continuity | Disaster recovery and backup procedures | 15% | 3 | 0.45 | Improvement areas identified
Geographic Risk | Political and operational stability | 10% | 4 | 0.4 | Low geographic risk
Regulatory Compliance | Adherence to relevant regulations | 10% | 4 | 0.4 | Good compliance record
Total Score |  | 100% |  | 3.6 | Medium-High risk level
Contract Element | DORA Requirement | Current Status | Gap Analysis | Required Action
Data Protection | Art. 30 - Data protection requirements | Partially compliant | Enhanced data protection clauses needed | Update contract with GDPR alignment
Audit Rights | Art. 30 - Right to audit ICT third-party providers | Limited audit rights | Full audit rights not established | Negotiate comprehensive audit clauses
Incident Notification | Art. 30 - Incident reporting requirements | Basic notification only | Detailed incident reporting missing | Add specific incident notification timelines
Exit Strategy | Art. 28 - Exit strategies for critical providers | No exit clause | Exit planning not addressed | Develop and include exit strategy provisions
Subcontracting | Art. 30 - Subcontracting approval and oversight | Limited visibility | Subcontractor management gaps | Require approval for critical subcontractors
Performance Monitoring | Art. 30 - Performance and availability monitoring | Basic SLAs only | Enhanced monitoring needed | Add detailed performance metrics and reporting
Business Continuity | Art. 30 - Business continuity and disaster recovery | General BC clauses | Specific recovery requirements missing | Include detailed BC and DR requirements
Termination Rights | Art. 30 - Termination rights and procedures | Standard termination | Enhanced termination rights needed | Add breach-based termination clauses
Due Diligence Area | Assessment Criteria | Risk Level | Status | Next Action
Legal and Regulatory | Regulatory compliance and legal standing | Low | Complete | Annual review scheduled
Financial Stability | Financial health and credit worthiness | Medium | Complete | Quarterly monitoring
Operational Capability | Service delivery and operational maturity | Medium | In Progress | Complete operational assessment
Information Security | Cybersecurity controls and risk management | High | In Progress | Security audit required
Data Management | Data handling and protection capabilities | High | Not Started | Data protection assessment needed
Business Continuity | Disaster recovery and business continuity | Medium | Not Started | BC capability assessment required
Geographic Risk | Political and operational location risks | Low | Complete | No action required
Concentration Risk | Dependency and concentration analysis | High | In Progress | Dependency mapping in progress
Exit Strategy Component | Description | Current Status | Target Completion | Owner
Data Migration Plan | Plan for extracting and migrating data | Not Started | 2024-12-31 | IT Operations Manager
Alternative Provider | Identification of alternative service providers | In Progress | 2024-11-30 | Vendor Risk Manager
Transition Timeline | Detailed timeline for service transition | Not Started | 2024-12-15 | Program Management Office
Knowledge Transfer | Documentation and knowledge transfer plan | Not Started | 2025-01-15 | IT Operations Manager
Contract Termination | Legal procedures for contract termination | In Progress | 2024-10-31 | Legal Department
Service Continuity | Plan to maintain service during transition | Not Started | 2024-12-31 | Business Continuity Manager
Cost Analysis | Financial impact analysis of exit scenario | Not Started | 2024-11-15 | Finance Department
Stakeholder Communication | Communication plan for exit scenario | Not Started | 2024-12-15 | Communications Manager

## Incident Management
Incident ID | Date | Time | Classification | Severity | Category | Description | Systems Affected | Business Impact | Detection Method | Response Time (mins) | Resolution Time (hrs) | Status | Root Cause | Lessons Learned
INC-2024-001 | 2024-08-01 | 14:30 | Major | High | System Outage | Core banking system unavailable | Core Banking Platform | Customer transactions blocked | Automated monitoring | 15 | 4.5 | Closed | Database connection failure | Improve connection pooling and monitoring
INC-2024-002 | 2024-08-03 | 09:15 | Minor | Medium | Performance | Slow response times in mobile app | Mobile Banking App | Degraded user experience | User complaints | 45 | 2 | Closed | High CPU utilization | Implement load balancing improvements
INC-2024-003 | 2024-08-05 | 16:20 | Major | Critical | Security | Suspicious login attempts detected | Authentication System | Potential data breach risk | SIEM alert | 5 | 8 | In Progress | Credential stuffing attack | Enhance rate limiting and MFA enforcement
Classification | Definition | Notification Timeline | Escalation Level | Regulatory Reporting Required
Minor | Limited impact on operations or customers | Within 4 hours | Department Manager | No
Moderate | Moderate impact on operations or customers | Within 2 hours | Senior Management | No
Major | Significant impact on operations or customers | Within 1 hour | Executive Management | Yes (if criteria met)
Critical | Severe impact threatening business continuity | Immediate (within 15 minutes) | Board/CEO | Yes
Response Team Role | Primary Contact | Backup Contact | Responsibilities | Activation Criteria
Incident Commander | John Smith (CISO) | Jane Doe (Deputy CISO) | Overall incident coordination and decision making | All Major and Critical incidents
Technical Lead | Mike Johnson (IT Ops Mgr) | Sarah Wilson (Senior Engineer) | Technical investigation and resolution | All incidents requiring technical expertise
Communications Lead | Lisa Brown (Comms Mgr) | Tom Davis (PR Manager) | Internal and external communications | Major and Critical incidents
Business Lead | Robert Chen (Business Mgr) | Emma Taylor (Deputy) | Business impact assessment and decisions | Incidents affecting business operations
Legal/Compliance | David Martinez (CLO) | Anna Rodriguez (Compliance) | Legal and regulatory requirements | Security incidents and regulatory reporting
Escalation Level | Timeline | Notification Recipients | Communication Method | Required Information
Level 1 - Team | Immediate | Incident response team | Slack/Teams | Basic incident details and status
Level 2 - Department | Within 30 minutes | Department management | Email + Phone | Impact assessment and response actions
Level 3 - Senior Management | Within 1 hour | Senior leadership team | Phone + Executive brief | Business impact and expected resolution
Level 4 - Executive | Within 2 hours | C-suite executives | Phone + Written report | Full incident details and media implications
Level 5 - Board | Within 4 hours | Board of directors | Secure communication | Complete incident briefing and next steps
Communication Template | Audience | Timing | Content Required | Approval Required
Initial Alert | Response Team | Immediate | Incident summary, systems affected, initial impact | Incident Commander
Status Update | Management | Every 30 minutes | Current status, actions taken, next steps, ETA | Technical Lead
Customer Communication | External | As needed | Service impact, expected resolution, alternative options | Communications Lead + Management
Regulatory Notification | Authorities | Within 72 hours (if required) | Detailed incident report, impact assessment, remediation | Legal/Compliance + Executive
Post-Incident Report | All Stakeholders | Within 5 business days | Root cause analysis, lessons learned, improvements | Incident Commander + Management
Recovery Objective | Definition | Target | Current Capability | Gap Analysis
RTO - Core Banking | Time to restore core banking services | 2 hours | 4 hours | Need faster recovery procedures
RPO - Transaction Data | Maximum acceptable data loss for transactions | 5 minutes | 15 minutes | Improve backup frequency
RTO - Mobile Banking | Time to restore mobile banking services | 1 hour | 2 hours | Enhance mobile platform resilience
RPO - Customer Data | Maximum acceptable data loss for customer data | 30 minutes | 1 hour | Implement real-time replication
RTO - Payment Systems | Time to restore payment processing | 30 minutes | 1 hour | Develop automated failover
RPO - Regulatory Data | Maximum acceptable data loss for regulatory reporting | 0 minutes | 5 minutes | Implement synchronous replication
Training Component | Target Audience | Frequency | Duration | Last Completed | Next Scheduled | Completion Rate
Incident Response Overview | All IT Staff | Annually | 2 hours | 2024-01-15 | 2025-01-15 | 85%
Technical Response Procedures | Technical Team | Quarterly | 4 hours | 2024-07-20 | 2024-10-20 | 90%
Crisis Communication | Management Team | Annually | 3 hours | 2024-02-10 | 2025-02-10 | 75%
Regulatory Reporting | Compliance Team | Semi-annually | 2 hours | 2024-06-15 | 2024-12-15 | 100%
Business Continuity | All Staff | Annually | 1 hour | 2024-03-01 | 2025-03-01 | 70%
Testing Scenario | Last Test Date | Test Result | Issues Identified | Remediation Actions | Next Test Date
Core System Failure | 2024-06-15 | Partial Success | Slow notification process | Automate alert system | 2024-09-15
Cyber Attack Response | 2024-07-20 | Success | Communication gaps | Improve escalation procedures | 2024-10-20
Data Center Outage | 2024-05-10 | Partial Success | Backup site delays | Enhance site readiness | 2024-08-10
Third-party Service Failure | 2024-04-25 | Needs Improvement | Vendor notification issues | Update vendor contracts | 2024-07-25
Regulatory Reporting Test | 2024-08-01 | Success | No issues identified | Continue current procedures | 2024-11-01